## Slide 1: Virtual Community Update
December 16, 2025

## Slide 2: Topics
Guest Presenters
Project Update
Commuter Options
Advancing the Rebuild
Pre-Construction Activities
Engagement
Questions & Answers

## Slide 3: Project Update

## Slide 4: Cost and Schedule
Updated Cost & Schedule
  Estimated cost range: $4.3–$5.2 billion
  Anticipated open-to-traffic: Late 2030
Early Cost Estimates
  Initial estimate developed less than two weeks after the collapse
  Required to secure federal funding with limited information
  Design was at 0%, with no engineering studies completed
Accelerated Progress
  In just 14 months, the project advanced to 70% design
  Progress typically takes 6–7 years on projects of this scale
  Pre-construction activities and updated data informed refined estimates

## Slide 5: Cost and Schedule
Key Cost Drivers
  Enhanced pier protection meeting federal safety requirements
  Higher and longer main-span to accommodate marine traffic
  Volatile construction market conditions
Modern Standards & Requirements
  Designed to meet modern design standards, federal requirements, national best practices
  Federal navigation clearance requirements, including a 230-foot height

## Slide 6
2018
JAN –
JUN
JUL -
DEC
2019
JAN –
JUN
JUL -
DEC
2020
JAN –
JUN
JUL -
DEC
2021
JAN –
JUN
JUL -
DEC
2022
JAN –
JUN
JUL -
DEC
2023
JAN –
JUN
JUL -
DEC
2024
JAN –
JUN
JUL -
DEC
2025
JAN –
JUN
JUL -
DEC
Francis Scott Key Bridge
15%
70%
PROJECT COST:
$1.9B
$4.3-5.2B
30%
60%
Mobile River Bridge
PROJECT COST:
$1.26B
$1.5B
$2.1B
?
Brent Spence Bridge
PROJECT COST:
$2.8B
?
$3.6B
30%
60%
Gordie-Howe Bridge
$2.68B
$4.64B
PROJECT COST:
30%
Open to Traffic

## Slide 7: Cost and Schedule
Construction Moving Forward
  Construction expected to begin next year, with efforts underway to address Baltimore-area traffic impacts
Commitment to Delivery
  Teams are working around the clock to deliver a safe, modern bridge the community can be proud of
Strong Federal & Project Partnerships
  Ongoing coordination with FHWA and design partner Kiewit on permitting, design, cost, and schedule
Protecting Taxpayers
  Maryland continues pursuing responsible parties to recover reconstruction costs and minimize taxpayer burden

## Slide 8: Traffic and Travel Impacts
Thank you for adjusting routes, carpooling, and using transit
Traffic has shifted to the Fort McHenry and Harbor tunnels
Expect longer rush hours and delays on I-95 and I-895
Traffic is monitored daily, with temporary solutions in place
Targeted toll and roadway adjustments are helping improve traffic flow

## Slide 9: Managing Mobility Post FSK Impact
December 16, 2025​

## Slide 10: Goal: Relieve Impacts to Commuters
Helping Travelers Post-FSK Bridge Collapse:
Best real-time information possible
Adjust transport operations
Providing new travel options
Deliver Measurably Better Benefits:
Reducing congestion
Increase convenience
Minimize impacts on local communities

## Slide 11: Related Mobility Offerings
Commuter Choice Maryland free commuter benefits (resources and incentives)
Transit Royale App provides real-time arrival information across transit modes
CHART Travel Time Website displays travel routes and travel times
Signalization and Timing Improvements to 30 signals during the initial 5-month period following the bridge collapse

## Slide 12: Commuter Choice Maryland’s Free programs and tools!
Baltimorecommutes.org
Commuters, visit:
Employers, contact:
commuterchoice@mdot.state.md.us

## Slide 13: Ride Together Rewards: Transit Incentives Program, Carpool Incentive Program, Vanpool Incentive Program
MDOT’s new Transit Incentive Program is making it easier to ride the bus and train in the Greater Baltimore area with two new incentives.
  Commuter Incentive: During select promotional periods, new transit users can download the CharmPass mobile app and receive FREE transit passes.
  Employer Incentive: Employers can receive up to $3,000 to purchase transit passes for your employees through the FareShare program.
Unlock a new commute with the Vanpool Incentive Program.
  Vanpools in the Baltimore region now qualify for a $500 monthly incentive through the new Baltimore Commutes Vanpool Incentive Program!
Utilize the Carpool Incentive Program for your commute and earn rewards for the first 90 days!
  Employees who carpool to work in the Baltimore region now qualify for a $5 daily incentive during a 90-day special incentive period through the new Baltimore Commutes Carpool Program!
Visit: BaltimoreCommutes.org or mdot.maryland.gov/transitincentives

## Slide 14: Ongoing Effort to ID New Actions
Coordination with TSO, SHA, MTA, MDTA and Local Jurisdictions, Partner Employers
Areas coming online:
  New transit incentive programs
  Physical infrastructure enhancements
  Targeted Corridor benefits
  Increased engagement with employers

## Slide 15: Join up to improve the commute!
Commuter Connections
tdm.commuterconnections.org/mwcog/

## Slide 16: Advancing the Rebuild

## Slide 17: Delivering the Safe and Efficient Reconstruction of the Key Bridge
*SCHEDULE IS SUBJECT TO CHANGE

## Slide 18: Typical Roadway Section
The roadway has two 12-foot lanes in each direction, with a 10-footoutside shoulder and 4-foot inside shoulder, meeting Interstate standards.
A 5-foot maintenance walkway runs along each side of the cable-stayed span, with cables set back from traffic for safety and improved wind stability.
Barriers are 42” tall to comply with current safety standards.

## Slide 19: Cable-Stayed Bridge
The cable-stayed bridge is 3,365 feet long and supported by six piers, including the two main pylons.
The 1,665-foot main span is the longest cable-stayed span in the U.S. and provides 230 feet of clearance for marine traffic.
The bridge is supported by 144 cables, which distribute the deck’s weight evenly.
Each pylon tower rises over 600 feet above the river, with a column that tapers as it ascends.

## Slide 20: Pylon Foundations
Each foundation is supported by 45 massive steel piles, each over 200 feet long and 8 feet in diameter, anchored deep into the Patapsco geological layer.​
The footing itself is roughly the size of two NBA basketball courts and stands 20 feet thick.​
More than 13,000 cubic yards of concrete—about 26,600 tons—goes into each footing.​
Constructing each foundation takes over 1,300 truckloads of concrete, placed in three layers.

## Slide 21: Cable-stayed Bridge Foundations
The cable-stayed bridge foundations include six total piers.​
​This includes the two main pylons along with a tie-down and transition pier on each side of the main span. ​
​Tie-down piers and transition piers each have 10 steel piles that are 8 feet in diameter in every foundation.​
​In total, the cable-stayed bridge foundations use 130 piles, each 8 feet in diameter.

## Slide 22: Pier Protection System
Each main pylon protection fender is longer and wider than an NFL football field and over 20 feet thick
Each of these foundations is supported by 78 steel pipe piles, each 8 feet in diameter
In total, the bridge’s vessel protection system uses 276 concrete-filled steel piles, each 8 feet in diameter.

## Slide 23: Pre-Construction Activities

## Slide 24: Geotechnical Borings​
Investigation program included land and marine borings which are deep, narrow holes drilled into the ground to collect soil samples ​
Samples provide data to develop safe, durable, and efficient structures tailored to site-specific ground conditions
The boring program is complete

## Slide 25: Wind Tunnel Testing
Simulated real-world wind conditions to study how the structure responds​
Fine-tuned the bridge shape, ensuring it will withstand powerful winds and extreme weather, even with heavy traffic

## Slide 26: Scour Testing
Simulated real-world water flow around piles to study how the riverbed responds​
Identified potential challenges like scour
Informed the pile design, ensuring it can withstand the impact of scour

## Slide 27: Mechanical Demolition
Mechanical demolition is using heavy machinery to remove existing bridge structures​
Land and over water demolition will occur in separate phases
Land demolition began in July 2025

## Slide 28: Test Pile Program
Test pile driving is used to advance the design of the main span foundations​
Periodic test pile driving began in October 2025 and is expected to continue through early 2026
Test piles are 8 feet in diameter and over 200 feet in length

## Slide 29: Trestle Construction
Work is underway at Hawkins Point to prepare for a temporary work platform or trestle.
The trestle will let supplies, labor, and equipment reach the pier sites more efficiently, speeding up construction.
In December, crews will begin driving piles to extend a trestle from Hawkins Point.
In early 2026, crews will start building a second trestle from Sollers Point.

## Slide 30: Safety on the Water
Safety remains the top priority as trestle and production pile work ramps up.
Safety Zone – No Entry Area is in effect; coordinated with the USCG since July 2025.
6-Knot No Wake Zone established in August 2025 to protect boaters and construction crews.
Federal Channel remains open, with no speed restrictions.

## Slide 31: Engagement

## Slide 32: Opportunities with Kiewit
Phase 1 of the project is approaching completion
Kiewit will begin soliciting subcontractor pricing (in Q4 2025) for inclusion in the Phase 2 cost estimate
Kiewit is currently seeking to engage with local and small firms interested in subcontracting opportunities on the Project

## Slide 33: Access Bid Opportunities
View the list of current solicitations and indicate the scope packages your company is interested in bidding at: https://bit.ly/KeyBridge-BidderInterest
* Bid opportunities are updated regularly. Please be sure to resubmit a bidder interest form to indicate your interest as scope packages are issued.
Scan the QR code to join our subcontractor and supplier database.
Express Your Bidding Interest*

## Slide 34: Engagement
100+ pop-up events
50+ speaking engagements​
860+ surveys taken
6,180+ connections with communities
4,200+ email subscribers
26,000+ Facebook subscribers

## Slide 35: Be on the look out!
Bridging the Facts Facebook series
Weekly Key Bridge Brief eblast
KEYnected Project Newsletter

## Slide 36: Stay Connected
Sign up for project alerts by email or text
Invite us to speak in your community
Share feedback through email or project hotline
Follow us on Facebook for project updates
Key Bridge Rebuild 2310 Broening Highway Baltimore, MD 21224
800-515-7030
Public Information Hotline
info@KeyBridgeRebuild.com
KeyBridgeRebuild.com
@KeyBridgeRebuild